## Sheet1
Task | 2021 |  | 2022
| Nov | Dec | Jan | Feb | March | April | May | june | july | Aug | sep | oct | nov | Dec
Research Topic Selection
Topic assesement
Project charter
Project proposal document
Project proposal presentation
Designing wireframes and mockups
ER and Hogh level architecture dessign
Software Implementation
Unit testing level 01
System integration testing level 01
Project Status Document 01
Progress presentation 01
Writing research paper
Testing level 02
Final report
Progress presentation 02
Demo level 1
Poster
Website Assesment
Project status document 02
Logbook
Final Presentation and Viva
Poster
Demo level 2
Final Thesis
Final report (Hard bound)